## Test case
TC No | Section/Path | Test Case Description | Test Data | Expected Result | Actual Result | Test Status | Added By | Screenshot | Comment
TC_001 | User Authentication | Test the user authentication process....by verifying that users can successfully sign up and log in. | test data was an users mail | received an otp, after using otp there will be a signup page then fillup the name & number section and singup willbe done | signup & loging process done succesfully using otp | Pass | Efty
TC_002 | Content Categories | Verify that content categories are accessible and correctly organized. |  | Organised | Organised | Pass | Efty
|  | Funny videos are not available |  | show different content on searching funny videos | show different content on searching funny videos | Fail
TC_003 | Video Streaming | Test the video streaming functionality for different types of content. |  | streaming functionality quite good as expected | streaming functionality quite good as expected | Pass | Efty
|  | Verify that videos load quickly and play smoothly without buffering issues. |  | load quick & play smooth | load quick & play smooth | Pass | Efty
|  | Check for features like pause, play, and autoplay. |  | All features are work properly | All features are work properly | Pass | Efty
TC_004 | Unique Video Content | Verify that the content available on the app is unique and aligns with Islamic principles. |  | content available on the app is unique and aligns with Islamic principles | content available on the app is unique and aligns with Islamic principles | Pass | Efty
|  | Check for any duplicate or inappropriate content. |  | no duplicate or inappropriate content. | no duplicate or inappropriate content. | Pass | Efty
TC_005 | Download Functionality | Test the download functionality for the videos. |  | download functionality not working yet | show a messege " coming soon" | Fail | Efty
|  | Verify that users can download videos for offline viewing. |  | As download functionality not working yet,this feature can't be available untill download function worked | not available yet | Fail | Efty
|  | Confirm that downloaded videos play correctly without any issues. |  | As download functionality not working yet,this feature can't be available untill download function worked | not available yet | Fail | Efty
TC_006 | Search and Filters | Test the search functionality to ensure users can find specific content |  | execute properly | execute properly | Pass | Efty
TC_007 |  | Verify that filters (e.g., by category, date, or popularity) work as expected. |  | this feature is not available yet | not available yet | Fail | Efty
TC_008 | User Interaction | Verify that user interactions are reflected correctly, and notifications (if any) are generated appropriately. |  | execute properly (notification feature not available yet) | execute properly | Pass
|  | Check for features that allow users to like, comment, or share videos |  | execute properly | execute properly | Pass | Efty
TC_009
TC_010
TC_011
TC_012
TC_013
TC_014
TC_015
TC_016
TC_017
TC_018
TC_019
TC_020
TC_021
TC_021
TC_022
TC_023

## Bug report
Section/Path | Bug/Concern Description | Status | Priority | Tester Name | Developer Name | Screenshot | Comment
Content Categories | Funny videos are not available | New | Low | Efty | Asad
Download Functionality | download functionality not working yet show messege coming soon | New | High | Efty | Asad
Download Functionality | Offline view not possible | New | High | Efty | Asad
Download Functionality | Can't play downloaded videos correctly without any issues. | New | High | Efty | Fahim
Search and Filters | Filters not (e.g., by category, date, or popularity) work as expected. | New | Medium | Inzamam | Fahim
Test Done
Phase 4
Dev Done